# Initial Project Planning Template

| Date | 19 July 2026 |
| --- | --- |
| Team ID | xxxxxx |
| Project Name | BookStore - Full-Stack E-Commerce Application (MERN Stack) |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

BookStore (MERN Stack) product backlog, organized into 4 two-week sprints covering authentication, catalog & search, cart & checkout, order tracking, reviews, and the admin dashboard. Total estimated story points: 56. "Team Members" is left blank for the team to assign.

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members | Sprint Start Date | Sprint End Date (Planned) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration | USN-1 | As a user, I can register for the application by entering my name, email, and password, and confirming my password. | 2 | High |  | 20 Jul 2026 | 02 Aug 2026 |
| Sprint-1 |  | USN-2 | As a user, my password is securely hashed (bcryptjs) so that my credentials are never stored in plain text. | 1 | High |  | 20 Jul 2026 | 02 Aug 2026 |
| Sprint-1 | Login | USN-3 | As a user, I can log into the application by entering my registered email & password. | 1 | High |  | 20 Jul 2026 | 02 Aug 2026 |
| Sprint-1 |  | USN-4 | As a user, I receive a JWT token on successful login so that I stay authenticated across requests. | 2 | High |  | 20 Jul 2026 | 02 Aug 2026 |
| Sprint-1 |  | USN-5 | As a user, I can log out of the application, clearing my session token. | 1 | Medium |  | 20 Jul 2026 | 02 Aug 2026 |
| Sprint-1 | Profile | USN-6 | As a user, I can view my profile details after logging in. | 1 | Medium |  | 20 Jul 2026 | 02 Aug 2026 |
| Sprint-1 | Book Catalog | USN-7 | As a user, I can browse a paginated catalog of all available books. | 3 | High |  | 20 Jul 2026 | 02 Aug 2026 |
| Sprint-1 |  | USN-8 | As a user, I can view detailed information about a single book, including price, stock, and rating. | 2 | High |  | 20 Jul 2026 | 02 Aug 2026 |
| Sprint-2 | Search & Filter | USN-9 | As a user, I can search for books by title, author, or genre. | 3 | High |  | 03 Aug 2026 | 16 Aug 2026 |
| Sprint-2 |  | USN-10 | As a user, I can filter books by price range and minimum rating. | 2 | Medium |  | 03 Aug 2026 | 16 Aug 2026 |
| Sprint-2 |  | USN-11 | As a user, I can sort books by price, rating, or newest arrivals. | 2 | Medium |  | 03 Aug 2026 | 16 Aug 2026 |
| Sprint-2 | Cart | USN-12 | As a user, I can add a book to my shopping cart. | 2 | High |  | 03 Aug 2026 | 16 Aug 2026 |
| Sprint-2 |  | USN-13 | As a user, I can update the quantity of an item already in my cart. | 1 | Medium |  | 03 Aug 2026 | 16 Aug 2026 |
| Sprint-2 |  | USN-14 | As a user, I can remove an item from my cart. | 1 | Medium |  | 03 Aug 2026 | 16 Aug 2026 |
| Sprint-2 |  | USN-15 | As a user, I can view my cart total before proceeding to checkout. | 1 | Medium |  | 03 Aug 2026 | 16 Aug 2026 |
| Sprint-3 | Checkout & Orders | USN-16 | As a user, I can check out my cart by providing a shipping address and payment method. | 3 | High |  | 17 Aug 2026 | 30 Aug 2026 |
| Sprint-3 |  | USN-17 | As a user, the system validates stock availability and automatically updates inventory when I place an order. | 3 | High |  | 17 Aug 2026 | 30 Aug 2026 |
| Sprint-3 | Order Tracking | USN-18 | As a user, I can view a list of my past orders. | 2 | High |  | 17 Aug 2026 | 30 Aug 2026 |
| Sprint-3 |  | USN-19 | As a user, I can view the current status of an order (Processing / Shipped / Delivered). | 2 | Medium |  | 17 Aug 2026 | 30 Aug 2026 |
| Sprint-3 |  | USN-20 | As a user, I can cancel an order while it is still in Processing status. | 2 | Medium |  | 17 Aug 2026 | 30 Aug 2026 |
| Sprint-3 | Reviews & Ratings | USN-21 | As a user, I can leave a star rating and written review for a book. | 2 | High |  | 17 Aug 2026 | 30 Aug 2026 |
| Sprint-3 |  | USN-22 | As a user, I can edit or delete my own review. | 1 | Low |  | 17 Aug 2026 | 30 Aug 2026 |
| Sprint-3 |  | USN-23 | As a user, I can view all reviews and the average rating for a book. | 1 | Medium |  | 17 Aug 2026 | 30 Aug 2026 |
| Sprint-4 | Admin - Manage Books | USN-24 | As an admin, I can add a new book with details and a cover image to the catalog. | 3 | High |  | 31 Aug 2026 | 13 Sep 2026 |
| Sprint-4 |  | USN-25 | As an admin, I can update an existing book's details, price, stock, or image. | 2 | High |  | 31 Aug 2026 | 13 Sep 2026 |
| Sprint-4 |  | USN-26 | As an admin, I can delete a book from the catalog. | 1 | Medium |  | 31 Aug 2026 | 13 Sep 2026 |
| Sprint-4 | Admin - Manage Orders | USN-27 | As an admin, I can view all customer orders across the platform. | 2 | High |  | 31 Aug 2026 | 13 Sep 2026 |
| Sprint-4 |  | USN-28 | As an admin, I can update an order's status and payment status. | 2 | High |  | 31 Aug 2026 | 13 Sep 2026 |
| Sprint-4 | Admin - Dashboard | USN-29 | As an admin, I can view a dashboard summarizing total books, total orders, and revenue. | 3 | Medium |  | 31 Aug 2026 | 13 Sep 2026 |
| Sprint-4 | Profile | USN-30 | As a user, I can update my name and shipping address in my profile. | 2 | Low |  | 31 Aug 2026 | 13 Sep 2026 |